## Summary
KodeEnd IT Solutions AB
Project Name | : | Better Return
Project Manager | : | Shahnawaz Jinnah
Project ID | : | N/A
Tester | : | Md. Golam An Nihal
Test Case Preparation Date | :
Version | : | 1
Total Test case | : | 53
Test case with steps | : | 53
Total Passed test case | : | 31
Total Failed test case | : | 18
Total blocked/out of scope test case | : | 4
Total untested/not executed | : | 0
Total | : | 53

## Report
Test Case Report
Project Name | Better Retuen
Module Name | Sign Up, Login, Account |  |  |  |  | Total No. | Status | Result :
Test Case Version | 1 |  |  |  |  | 31 | PASS
Written By | Md. Golam An Nihal |  |  |  |  | 18 | FAIL
Executed By | Md. Golam An Nihal |  |  |  |  | 0 | Not Executed | New Features | Testing Scope | Testing Environment : | Google Chrome Browser
Reviewed By | Shahnawaz Jinnah |  |  |  |  | 4 | Out of Scope
TEST EXECUTION REPORT
Test Case | PASS | FAIL | Not Executed | Out Of Scope | Total TC
| 31 | 18 | 0 | 4 | 53
Grand Total | 31 | 18 | 0 | 4 | 53
LIMITATIONS
Documents |  |  |  | Received | Useful
PRD |  |  |  | No | No
USER STORY |  |  |  | No | No
| Testing Type in Scope | Description
Yes/ No. Justification (If No): | Functional Testing | This type of testing ignores the internal parts and focuses only on the output to check if it is as per the requirement or not.
Yes/ No. Justification (If No): | Integration Testing | Testing of all integrated modules to verify the combined functionality after integration is termed as Integration Testing.
Yes/ No. Justification (If No): | Negative Testing | Testing having the mindset of “attitude to break” using incorrect data and invalid inputs.
Yes/ No. Justification (If No): | Usability Testing | Test application from user friendliness perspective.
Yes/ No. Justification (If No): | Browser Compatibility Testing | Browser Compatibility Testing is performed for web applications and it ensures that the software can run with the combination of different browser and operating system. This type of testing also validates whether web application runs on all versions of all browsers or not.
Yes/ No. Justification (If No): | Boundary Value Testing | There is an upper and lower boundary for each range and testing is performed on these boundary values.
Yes/ No. Justification (If No): | Risk Based Testing Or Regression Testing | Risk-Based Testing includes testing of highly critical functionality, which has the highest impact on business and in which the probability of failure is very high. Testing an application as a whole for the modification in any module or functionality is termed as Regression Testing.

## TestCase
Product Name |  | Better Return | TC Start Date | 21/5/2023 | TC Execution Start Date | 23/05/2023 |  |  |  |  | TEST CASE
Module Name |  | Sign Up, Login, Account | TC End Date | 22/5/2023 | TC Execution End Date | 26/05/2023 |  |  |  |  | PASS | 31
Epic |  | N/A | Test Case Developed By | Md. Golam An Nihal | Browser (tested) | Yes |  |  |  |  | FAIL | 18
Developer Name (TL) |  |  | Test Case Reviewed By | Shahnawaz Jinnah | Performance (tested) | No |  |  |  |  | Not Executed | 0
Test Executed by | [10 empty] | Out of Scope | 4
[11 empty] | TOTAL | 53
Test Case No. | Module | Type of Testing | Features | Test Cases | Exepected Result | Actual Result | Test Data | Reproducing Steps | Bug Screen Shot | Dev Comments | Final Status | Remarks
TC1 |  | Browser Compatibility Testing |  | Checking by running the site in different browsers | Should run in different browsers | Found as per expectation | Chrome Internet Explorer Mozilla Firefox Microsoft Edge Opera Mini | 1. Goto different browsers 2. Search 'BD Shop' 3. Goto the website |  |  | Passed
TC2 | User Management | UI Testing | Sign Up | Checking spelling or grammatical mistakes | No spelling or grammatical mistakes | Found as per expectation | N/A | 1. Goto the URL https://betterreturn.net/ 2. Click on Sign Up button at the right corner 3. Check the spelling and grammar of the website |  |  | Passed
TC3 |  |  |  | Verifying the font, text color and style | Should be as per the requirement | Found as per expectation | N/A | 1. Goto the URL https://betterreturn.net/ 2. Click on Sign Up button at the right corner 3. Check the font, text color and style |  |  | Passed
TC4 |  |  |  | Verifying mandatory field is marked with a red asterisk | Red asterisk should be present | Not found as per expectation | N/A | 1. Goto the URL https://betterreturn.net/ 2. Click on Sign Up button at the right corner 3. Check red asterisk beside mandatory field | Red Asterisk not present error |  | Failed
TC5 |  |  |  | Checking by hovering over the fields | A text should appear over the fields | Not found as per expectation | N/A | 1. Goto the URL https://betterreturn.net/ 2. Click on Sign Up button at the right corner 3. Hover over every fields | Hovering text error |  | Failed
TC6 |  |  |  | Checking alignment of the fields | Proper alignment of the fields should be present | Found as per expectation | N/A | 1. Goto the URL https://betterreturn.net/ 2. Click on Sign Up button at the right corner 3. Check alignment of the fields |  |  | Passed
TC7 |  |  |  | Checkbox beside 'Remember Me' | Checkbox should be present | Remember me checkbox isn't present | N/A | 1. Goto the URL https://betterreturn.net/ 2. Click on Sign Up button at the right corner 3. Check checkbox beside 'Remember Me' | Remember me' checkbox errror |  | Out of Scope
TC8 |  |  |  | Checking 'Remember Me' checkbox is not enabled by default | Should not be enabled by default | Remember me checkbox isn't present | N/A | 1. Goto the URL https://betterreturn.net/ 2. Click on Sign Up button at the right corner 3. Check 'Remember Me' checkbox | Remember me' checkbox errror |  | Out of Scope
TC9 |  | Functional Testing |  | Keeping mandatory fields blank | Should be as per the requirement | Sholud not allow user to register and pop an error message | N/A | 1. Goto the URL https://betterreturn.net/ 2. Click on Sign Up button at the right corner 3.Keep mandatory fields blank |  |  | Passed
TC10 |  |  |  | Checking name field is case insensitive | Should accept the provided input | Found as per expectation | XXx | 1. Goto the URL https://betterreturn.net/ 2. Click on Sign Up button at the right corner and create account 3. Give the provided username |  |  | Passed
TC11 |  |  |  | Entering blank at name field | Should not accept the provided input | Found as per expectation |  | 1. Goto the URL https://betterreturn.net/ 2. Click on Sign Up button at the right corner and create account 3. Keep the name field blank |  |  | Passed
TC12 |  |  |  | Checking alert message for all mandatory fields | Should pop an error message | Not found as per expectation | N/A | 1. Goto the URL https://betterreturn.net/ 2. Click on Sign Up button at the right corner and create account 3. Keeping blank in each field and checking repeatedly | No alert message error |  | Failed
TC13 |  |  |  | Inputing name with special characters | Should not accept the provided input | Not found as per expectation | !@#$% | 1. Goto the URL https://betterreturn.net/ 2. Click on Sign Up button at the right corner and create account 3. Enter special characters in name field | Special character error |  | Failed
TC14 |  |  |  | Inputing name with numbers | Should not accept the provided input | Not found as per expectation | 55 | 1. Goto the URL https://betterreturn.net/ 2. Click on Sign Up button at the right corner and create account 3. Enter numbers in name field | Numbers error |  | Failed
TC15 |  |  |  | Inputing name with decimal numbers | Should not accept the provided input | Not found as per expectation | 55.5 | 1. Goto the URL https://betterreturn.net/ 2. Click on Sign Up button at the right corner and create account 3. Enter decimal numbers in name field | Decimal numbers error |  | Failed
TC16 |  |  |  | Inputing name with alphanumeric characters | Should accept the provided input | Found as per expectation | John88 lizz44 | 1. Goto the URL https://betterreturn.net/ 2. Click on Sign Up button at the right corner and create account 3. Enter alphanumeric characters in name field |  |  | Passed
TC17 |  |  |  | Inputing name with alphabets | Should accept the provided input | Found as per expectation | John Austin | 1. Goto the URL https://betterreturn.net/ 2. Click on Sign Up button at the right corner and create account 3. Enter alphabets in name field |  |  | Passed
TC18 |  |  |  | Entering space between alphabets for name | Should accept the provided input | Found as per expectation | John Braitt Austin Jane | 1. Goto the URL https://betterreturn.net/ 2. Click on Sign Up button at the right corner and create account 3. Enter space between alphabets name field |  |  | Passed
TC19 |  |  |  | Entering invalid phone number | Should not accept invalid phone numbers | Accpets invalid phone and no validation of phone number | 01701013335dsfsafsadad | 1. Goto the URL https://betterreturn.net/ 2. Click on Sign Up button at the right corner and create account 3. In next page use the provided phone and click continue | Invalid phone error |  | Failed
TC20 |  |  |  | Entering text in country code input box of phone | Should not accept invalid country code | Accpets invalid country code and no validation of country code | Bangl | 1. Goto the URL https://betterreturn.net/ 2. Click on Sign Up button at the right corner and create account 3. In next page use the provided country code in phone and click continue | Invalid country code error |  | Failed
TC21 |  |  |  | Validating an email id can only be used one time | Should not allow user to register and display a pop message | Found as per expectation with an error message | annihal55@gmail.com | 1. Goto the URL https://betterreturn.net/ 2. Click on Sign Up button at the right corner 3. Fill the email address with already registered email |  |  | Passed
TC22 |  |  |  | Checking by inputing invalid email format | Should not accept the provided input and display an error message | Not found as per expectation | email: AB@CD | 1. Goto the URL https://betterreturn.net/ 2. Click on Sign Up button at the right corner 3. Fill the email address with invalid email address format | invalid email format error |  | Failed
TC23 |  |  |  | Checking by inputing valid email format | Should accept the provided input | Found as per expectation | tamannasana44@gmail.com | 1. Goto the URL https://betterreturn.net/ 2. Click on Sign Up button at the right corner 3. Fill the email address with valid email address format |  |  | Passed
TC24 |  |  |  | Checking password field values are masked | Should be masked | Found as per expectation | john8888 | 1. Goto the URL https://betterreturn.net/ 2. Click on Sign Up button at the top right corner 3. Enter password |  |  | Passed
TC25 |  |  |  | Inputing weak password length | Should allow user to register | Found as per expectation | hhg#k88 | 1. Goto the URL https://betterreturn.net/ 2. Click on Sign Up button at the top right corner 3. Enter weak password length in password |  |  | Passed
TC26 |  |  |  | Inputing medium password length | Should allow user to register | Found as per expectation | hjfyvj%975 | 1. Goto the URL https://betterreturn.net/ 2. Click on Sign Up button at the top right corner 3. Enter medium password length in password |  |  | Passed
TC27 |  |  |  | Inputing strong password length | Should allow user to register | Found as per expectation | hgjkgjkjkjh!&*77 | 1. Goto the URL https://betterreturn.net/ 2. Click on Sign Up button at the top right corner 3. Enter strong password length in password |  |  | Passed
TC28 |  |  |  | Check 'confirm password' text field | Should allow user to retype and confirm their password | Confirm password isn't present |  | 1. Goto the URL https://betterreturn.net/ 2. Click on Sign Up button at the top right corner 3. Check for confirm password text field | confirm password' textfield missing |  | Out of Scope
TC29 |  |  |  | Inputing invalid or very short length for password | Should not allow user to register | Not found as per expectation | password: a | 1. Goto the URL https://betterreturn.net/ 2. Click on Sign Up button at the top right corner 3. Enter 'a' in password field | invalid password error |  | Failed
TC30 |  |  |  | Checking registration with invalid email address | Should not allow user to register and pop an error message | Not found as per expectation | Email: abc@def.com Password: abc | 1. Goto the URL https://betterreturn.net/ 2. Click on Sign Up button at the top right corner 3. Fill all the fiels with invalid credentials 4.Click 'Create an Account' | Invalid email address error |  | Failed
TC31 |  |  |  | Checking registration button with valid credentials | Should allow user to register | Found as per expectation | Email: annihal55@gmail.com Password: abc1233@$# | 1. Goto the URL https://betterreturn.net/ 2. Click on Sign Up button at the top right corner 3. Fill all the fiels with valid credentials 4.Click 'Create an Account' |  |  | Passed
TC32 |  |  |  | Checking confirmation mail sent to the registered email | Sent successfully | Not found as per expectation | Email: annihal55@gmail.com Password: abc | 1. Goto the URL https://betterreturn.net/ 2. Click on Sign Up button at the top right corner 3. Fill all the fiels with valid credentials 4.Create an Account 5. Check mail and confirm account |  |  | Failed
TC33 |  | Usability Testing |  | Checking copy paste functionality in every field | Should copy and paste text from fields | Functioning successfully | jane9999 | 1. Goto the URL https://betterreturn.net/ 2. Click on Sign Up button at the top right corner 3. Copy paste text in every field |  |  | Passed
TC34 |  |  |  | Checking keyboard tab button functionality | Should switch to another field and highlight text | Functioning successfully | Enter tab in every field | 1. Goto the URL https://betterreturn.net/ 2. Click on Sign Up button at the top right corner 3. Enter tab in every field |  |  | Passed
TC35 |  |  |  | Checking keyboard enter button functionality | Should switch to another field | Functioning successfully | Input Enter in every field | 1. Goto the URL https://betterreturn.net/ 2. Click on Sign Up button at the top right corner 3. Enter enter in every field |  |  | Passed
TC36 |  | Functional Testing | Log In | Keeping email and password field blank | Should not allow user to login and display an error messeage | Found as per expectation | N/A | 1. Goto the URL https://betterreturn.net/ 2. Click on Log in button at the top right corner 3. Keep both the fields blank |  |  | Passed
TC37 |  |  |  | Checking if the data in password is masked | Should be masked | Found as per expectation | john@8888 | 1. Goto the URL https://betterreturn.net/ 2. Click on Log in button at the top right corner 3. Input values in password field and check if it is masked |  |  | Passed
TC38 |  |  |  | Checking login wrong credentials in email and password field | Should not allow user to login and display an error messeage | Found as per expectation | fgcfh@nndj.com hdjui44 | 1. Goto the URL https://betterreturn.net/ 2. Click on Log in button at the top right corner 3. Input invalid credentials in email and password field |  |  | Passed
TC39 |  |  |  | Checking login valid credentials in email and password field | Should allow user to register | Found as per expectation | Email: annihal55@gmail.com | 1. Goto the URL https://betterreturn.net/ 2. Click on Log in button at the top right corner 3. Input valid credentials in email and password field |  |  | Passed
TC40 |  |  |  | Verifying ‘Forgot Password’ functionality | Should sent an email for recovering password | Forgot password reset email doesn't repond sometimes and sometimes responses very late | N/A | 1. Goto the URL https://betterreturn.net/ 2. Click on Log in button at the top right corner 3.Click on 'Forgot Password' 4. Check email |  |  | Failed
TC41 |  |  |  | Checking by selecting ‘Forgot Password’ multiple times | Account should be temporarily restricted and a message should be displayed | Not found as per expectation | N/A | 1. Goto the URL https://betterreturn.net/ 2. Click on Log in button at the top right corner 3.Click on 'Forgot Password' multiple times |  |  | Failed
TC42 |  |  |  | Verifying change the password link is sent to valid email address | Should be sent to valid email address | Found as per expectation | N/A | 1. Goto the URL https://betterreturn.net/ 2. Click on Log in button at the top right corner 3.Click on 'Forgot Password' and provide the email 4. Check the registered email |  |  | Passed
TC43 |  |  |  | Verifying the functionality of 'Set a New Password' | Should provide a new input for setting new password | Found as per expectation | N/A | 1. Goto the URL https://betterreturn.net/ 2. Click on Log in button at the top right corner 3.Click on 'Forgot Password' and provide email 4. Check the registered email 5. Click on 'Set up a New Password' |  |  | Passed
TC44 |  |  |  | Enabling the 'Show Password' checkbox of 'Set a New Password' | Password should be dispayed | Found as per expectation | Email: annihal55@gmail.com | 1. Goto the URL https://betterreturn.net/ 2. Click on Log in button at the top right corner 3.Click on 'Forgot Password' 4. Check the registered email 5. Click on 'Set up a New Password' 6. Enable 'Show Password' checkbox |  |  | Passed
TC45 |  |  |  | Verifying inputing old password on 'Set a New Password' | Should not allow user to login and display an error message | User logs in with the old password. | Email: annihal55@gmail.com | 1. Goto the URL https://betterreturn.net/ 2. Click on Log in button at the top right corner 3.Click on 'Forgot Password' 4. Check the registered email 5. Click on 'Set up a New Password' 6. Enter old password |  |  | Failed
TC46 |  |  |  | Verifying login with the newly changed password | Should allow user to login | User logs in with the old password. Changed password doesn't work | Email: annihal55@gmail.com | 1. Goto the URL https://betterreturn.net/ 2. Click on Log in button at the top right corner 3.Click on 'Forgot Password' 4. Check the registered email 5. Click on 'Set up a New Password' 6. Enter new password 7. Click on login |  |  | Failed
TC47 |  |  |  | Checking if the link gets dissolved setting a new password | Link should get dissolved | Link doesn't dissolve even after the password is changed | N/A | 1. Goto the URL https://betterreturn.net/ 2. Click on Log in button at the top right corner 3.Click on 'Forgot Password' 4. Check the registered email 5. Click on 'Set up a New Password' 6. Enter new password 7. Click on 'Create New password' 8. Check if the reset password email is dissolved or not |  |  | Failed
TC48 |  | Functional Testing | Account | Verifying profile picure update | Should allow users to update their profile picture | Users can update | Email: abc@def.com Password: abc | 1. Goto the URL https://betterreturn.net/ 2. Click on Log in button at the top right corner 3. Give valid credentials and login 4. Go to account setting>account in the bottom left corner 5. Click on update profile picture icon and upload a picture from local machine |  |  | Passed
TC49 |  |  |  | Verifying username update | Should allow users to update their username | Users can update | Email: abc@def.com Password: abc | 1. Goto the URL https://betterreturn.net/ 2. Click on Log in button at the top right corner 3. Give valid credentials and login 4. Go to account setting>account in the bottom left corner 5.Give a new username and click on save settings |  |  | Passed
TC50 |  |  |  | Verifying email update | Should allow users to update their email | Email can't br changed or updated | Email: abc@def.com Password: abc | 1. Goto the URL https://betterreturn.net/ 2. Click on Log in button at the top right corner 3. Give valid credentials and login 4. Go to account setting>account in the bottom left corner 5. Click on email field and try to change |  | email not changeable error | Failed
TC51 |  |  |  | Verifying phone update | Should allow users to update their phone | Users can update | Email: abc@def.com Password: abc | 1. Goto the URL https://betterreturn.net/ 2. Click on Log in button at the top right corner 3. Give valid credentials and login 4. Go to account setting>account in the bottom left corner 5. Click on phone and try to change 6. Click on save settings |  |  | Passed
TC52 |  |  |  | Verifying password update | Should allow users to update their password | Users can update | Email: abc@def.com Password: abc | 1. Goto the URL https://betterreturn.net/ 2. Click on Log in button at the top right corner 3. Give valid credentials and login 4. Go to account setting>account in the bottom left corner 5. Click on password field and try to change 6. Click on save settings |  |  | Passed
TC53 |  |  |  | Verifying if users can confirm password before changing | Should allow users to confirm their password before changing | Confirm password isn't present | Email: abc@def.com Password: abc | 1. Goto the URL https://betterreturn.net/ 2. Click on Log in button at the top right corner 3. Give valid credentials and login 4. Go to account setting>account in the bottom left corner 5. Click on password field and try to change 6. Check if there is confirm password text field |  | confirm password text field missing error | Out of Scope
|  |  | Improvement Scopes | 'Remember Me' checkbox should be present during user login
A maximum length of the password should be defined
Forgot password reset email response should be improved
Confirm password functionality should be present for users
Negative test

## Test Metrics
Test Metrics
#SL | Metrics | Description | Result (%)
1 | Percentage of Test Cases Executed | (No. of Test Cases Executed / Total no. of Test Cases Written) * 100 | (53/53)*100 = 100
2 | Percentage of Test Cases Not Executed | (No. of Test Cases not Executed / Total no. of Test Cases Written) * 100 | (0/53)*100 = 0
3 | Percentage of Test Cases Passed | (No. of Test Cases Passed / Total no. of Test Cases Executed) * 100 | (31/53)*100 = 58.49
4 | Percentage of Test Cases Failed | (No. of Test Cases Failed / Total no. of Test Cases Executed) * 100 | (18/53)*100 = 33.96
5 | Percentage of Test Cases Blocked | (No. of Test Cases Blocked / Total no. of Test Cases Executed) * 100 | (4/53)*100 =7.55
6 | Defect Density | No. of Defects found / Size (No. of Requirements) | N/A
7 | Defect Removal Efficiency (DRE) | (Fixed Defects / (Fixed Defects + Missed Defects)) * 100 | N/A
8 | Defect Leakage | (No. of Defects found in UAT/ No. of Defects found in Testing) * 100 | N/A
9 | Defect Rejection Ratio | (No. of Defects Rejected/ Total no. of Defects Raised) * 100 | N/A
10 | Defect Age | Fixed date - Reported date | N/A
11 | Customer Satisfaction | No. of complaints per Period of Time | N/A